## Read me
Lumen Rollout · Project control workbook
Oracle EPM rollout (EPBCS and FCCS) at Maison Lumen · status at 25 September 2026
Purpose | One place for the registers the project manager reviews every week and presents to the steering committee.
Owner | Gaurav Sharma, project manager
Status date | 2026-09-25
Sheet | Content
Dashboard | Calculated summary: risks, issues, change control, UAT exit criteria and the go/no-go decision
Risks | Risk register: probability × impact, level, owner, response, status
Assumptions | What the plan takes for granted, with the date by which it must be checked
Issues | Risks that have happened, with an owner and an action
Dependencies | Work outside the project team; status calculated from the dates
Decisions | Decisions of the steering committee and of the project manager
Change log | Change requests, their impact, who decides, and the contingency released
UAT test plan | User acceptance test cases, traced to the requirements of the design documents
Defects | Defects raised in testing, by severity
Go-no-go | Cutover checklist for the EPBCS go-live
Legend | Yellow cells are inputs: edit them. Grey cells are formulas: do not overwrite them.
Risk scale | Score = P × I (1 to 5 each). Low 1–7, medium 8–14, high 15–25; 20 or more blocks the go-live.
Tolerances | Go-lives ±10 working days; cost +5 % of the authorised budget. Beyond them: exception report to the steering committee.
Change authority | Project manager up to 10 k€ with no effect on a go-live; otherwise the steering committee (COPIL).
Note | Portfolio sample. Maison Lumen, its people and all figures are fictional.

## Dashboard
Dashboard · status at 25 September 2026
Every value on this sheet is calculated from the registers.
RAID
Open risks
Open high risks (score 15 or more) | Go-live condition
Open risks blocking go-live (score 20 or more) | Go-live blocker
Open issues
Late dependencies
Change control
Change requests awaiting decision
Contingency left (k€)
Authorised budget (k€) | Work budget + contingency released
UAT
Test cases in scope
Passed
Failed
Blocked
Not run
Executed | Passed + failed, over cases in scope
Pass rate
Open critical defects
Open major defects
Security tests passed
Exit criteria
C1 · 100 % of cases executed
C2 · At least 95 % passed (90 % with conditions)
C3 · No critical defect open
C4 · No major defect (2 at most with a workaround)
C5 · 100 % of security tests passed
Go/no-go
Critical checklist actions not done | Blockers
Other checklist actions not done | Conditions
Blocking points | Exit criteria + critical actions + risks of 20 or more
Conditions | Exit criteria + other actions + high risks below 20
Calculated decision | Recorded by the go/no-go committee

## Risks
ID | Risk | Owner | P (1-5) | I (1-5) | Score | Level | Blocks go-live | Response | Action | Status
R1 | Poor quality of historical ERP data | IT / ERP | 4 | 4 |  |  |  | Reduce | Data cleansing and monthly reconciliation with accounting | Open
R2 | Key users unavailable during testing (budget season) | Sponsor (CFO) | 4 | 3 |  |  |  | Reduce | Test schedule approved by the CFO, half-days blocked | Open
R3 | Delay in the ERP data flows (Data Management) | IT / ERP | 3 | 4 |  |  |  | Fallback | Manual file loads until the flows are ready | Open
R4 | Complex consolidation rules (NCI, FX) | Consolidation team | 2 | 4 |  |  |  | Reduce | Dedicated test cases, auditor review | Open
R5 | Resistance to change (attachment to Excel) | Project manager | 3 | 3 |  |  |  | Reduce | Champions in each entity, demos, hands-on training | Open
R6 | Dependence on one key consultant | Project manager | 2 | 3 |  |  |  | Reduce | Documentation and pairing with the internal team | Open
R7 | Oracle's October update during testing (test 2 Oct, production 16 Oct) | IT / ERP | 3 | 2 |  |  |  | Accept | Regression tests after each update, before production | Open
R8 | Project budget overrun | Project manager | 3 | 3 |  |  |  | Reduce | Monthly earned value, scope trade-offs with the sponsor | Open

## Assumptions
ID | Assumption | Owner | Check by | Status | Note
AS1 | Key users give two half-days a week to testing | Sponsor (CFO) | 2026-09-14 | Confirmed
AS2 | The group chart of accounts stays frozen until the FCCS go-live | Consolidation team | 2026-05-15 | Confirmed
AS3 | Oracle EPM licences cover 60 users at no extra cost | IT / ERP | 2026-03-27 | Confirmed
AS4 | The 2024–2025 history can be extracted from the ERP without rework | IT / ERP | 2026-06-30 | False | Proved false: became issue I1

## Issues
ID | Issue | Priority | Owner | Action | Status
I1 | ERP flows about a month late: 2024–2025 history not yet loaded | High | IT / ERP | Manual loads for testing; escalated to the committee | Open
I2 | Since Oracle's 4 September update, journals are unavailable in the test environment | Medium | IT / ERP | Support request (SR) opened with Oracle | Open
I3 | Two key users absent the week of 5 October | Medium | Sponsor (CFO) | Stand-ins named by the CFO | Open

## Dependencies
ID | Dependency | Owner | Needed by | Forecast | Status
DP1 | ERP flows delivered by the ERP team before performance testing | IT / ERP | 2026-09-25 | 2026-09-25
DP2 | Test environment available after each Oracle update | IT / ERP | 2026-10-05 | 2026-10-02
DP3 | Closing exchange rates supplied by treasury before the parallel run | Consolidation team | 2026-11-30 | 2026-11-27
DP4 | FY27 budget calendar approved by executive management | Sponsor (CFO) | 2026-09-30 | 2026-10-09

## Decisions
Date | Forum | Decision
2026-03-27 | COPIL | Project charter approved: 480 k€ budget plus 48 k€ contingency; tolerances of ±10 working days on go-lives and +5 % on cost
2026-05-15 | COPIL | Design document signed off; CR-01 approved (FCCS go-live on the year-end close)
2026-07-03 | COPIL | CR-05 rejected: workforce planning moved to phase 2
2026-08-28 | COPIL | Build complete accepted; testing stage authorised
2026-09-08 | Project manager | CR-02 approved within the project manager's delegation (8 k€ of contingency)

## Change log
ID | Request | Type | Requested by | Date | Cost (k€) | Time (working days) | Change authority | Status | Contingency released (k€) | Note
CR-01 | Align the FCCS go-live on the year-end close (January) rather than December | Time | Consolidation team | 2026-05-15 | 0 | 20 |  | Approved |  | Baseline updated at design sign-off
CR-02 | Manual file loads for testing until the ERP flows are ready | Cost | IT / ERP | 2026-09-08 | 8 | 0 |  | Approved |  | Within the project manager's delegation
CR-03 | Release 30 k€ of contingency: ERP delay and extended testing | Cost | Project manager | 2026-09-22 | 30 | 0 |  | Submitted |  | Awaiting the steering committee
CR-04 | Defer the CFO dashboard (case U22) to phase 2 | Scope | FP&A key users | 2026-09-24 | 0 | 0 |  | Submitted |  | Reduces test scope; no go-live impact
CR-05 | Add driver-based workforce planning to phase 1 | Scope | FP&A key users | 2026-07-03 | 40 | 30 |  | Rejected |  | Incompatible with the budget calendar; phase 2
| Work budget (k€) | 480
| Contingency approved at charter (k€) | 48
Contingency released (k€)
Contingency left (k€)
Authorised budget (k€)

## UAT test plan
ID | Area | Test case | Requirement | Tester | Status | Open defect
U01 | Planning | Driver-based budget entry | REQ-02 | FP&A key users | Passed
U02 | Planning | Revenue = units × price | REQ-02 | FP&A key users | Passed
U03 | Planning | Payroll and 13th month | REQ-03 | FP&A key users | Failed | D1
U04 | Planning | Head-office cost allocation | REQ-04 | FP&A key users | Passed
U05 | Planning | Top-down spreading | REQ-05 | FP&A key users | Passed
U06 | Planning | Budget approval workflow | REQ-06 | FP&A key users | Passed
U07 | Planning | What-if simulation | REQ-07 | FP&A key users | Not run
U08 | Planning | Rolling 9+3 forecast | REQ-01 | FP&A key users | Not run
U09 | Consolidation | IAS 21 translation | FCCS design | Consolidation team | Passed
U10 | Consolidation | Intercompany matching | FCCS design | Consolidation team | Failed | D2
U11 | Consolidation | Automatic eliminations | FCCS design | Consolidation team | Passed
U12 | Consolidation | Goodwill and NCI | FCCS design | Consolidation team | Passed
U13 | Consolidation | Journals and approval | FCCS design | Consolidation team | Blocked | D5
U14 | Consolidation | Consolidated statements | FCCS design | Consolidation team | Not run
U15 | Consolidation | Close checks | FCCS design | Consolidation team | Not run
U16 | Data | Monthly ERP actuals load | REQ-08 | IT / ERP | Passed
U17 | Data | Mapping table and kick-outs | REQ-08 | IT / ERP | Passed
U18 | Data | Exchange rate load | FCCS design | IT / ERP | Not run
U19 | Data | 2024–2025 history reconciled | REQ-08 | IT / ERP | Blocked | D6
U20 | Reports | Budget variance report | REQ-09 | FP&A key users | Passed
U21 | Reports | Consolidation pack | FCCS design | FP&A key users | Not run
U22 | Reports | CFO dashboard | REQ-12 | FP&A key users | Not run
U23 | Security | Access restricted by entity | REQ-10 | IT / ERP | Failed | D4
U24 | Security | Approver profiles | REQ-10 | IT / ERP | Not run

## Defects
ID | Test case | Severity | Description | Owner | Status
D1 | U03 | Critical | The 13th month is not calculated in December for Paris | EPM consultant | Open
D2 | U10 | Major | FX differences are flagged 'to investigate' instead of 'FX difference' | EPM consultant | Open
D3 | U20 | Minor | Truncated label in the variance report | EPM consultant | Closed
D4 | U23 | Critical | A Lille controller can see Paris data | EPM consultant | Open
D5 | U13 | Major | Journals unavailable since Oracle's 4 September update (test environment) | IT / ERP | Open
D6 | U19 | Major | 2024 history incomplete: ERP flow not delivered | IT / ERP | Open

## Go-no-go
ID | Area | Action | Critical | Owner | Done
K1 | Data | 2024–2025 history loaded and reconciled | Yes | IT / ERP | No
K2 | Data | Exchange rates and opening balances approved | Yes | Consolidation team | Yes
K3 | Data | ERP mapping tables frozen | Yes | IT / ERP | Yes
K4 | Technical | ERP flows scheduled in production | Yes | IT / ERP | No
K5 | Technical | Application snapshot taken before cutover | Yes | EPM consultant | No
K6 | Technical | Production access rights checked by entity | Yes | EPM consultant | No
K15 | Technical | Mock cutover (dress rehearsal) completed, timings measured | Yes | IT / ERP | No
K16 | Technical | Regression tests passed after Oracle's October update | Yes | FP&A key users | No
K7 | Users | At least 90 % of users trained | Yes | Project manager | No
K8 | Users | User guides published | No | EPM consultant | Yes
K9 | Users | Champions named in each entity | No | Sponsor (CFO) | Yes
K10 | Support | Hypercare schedule approved | No | Project manager | Yes
K11 | Support | Oracle support (SR) procedure tested | No | IT / ERP | No
K12 | Governance | Test sign-off minutes signed by the sponsor | Yes | Sponsor (CFO) | No
K13 | Governance | Rollback plan documented | Yes | Project manager | Yes
K14 | Governance | Launch communication sent | No | Project manager | No